## 工作表1
Milestone | Objective | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August
Week |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Research | Robotics systematic tollbox | May 1: Exam
Kinematic | bar: March 3 to March 4
RRMC | bar: March 4 to April 1
Kinematic | Forward Kinematic | bar: March 2 to March 3
Inverse Kinematic | bar: March 4 to April 1
RRMC | Velocity vecto | bar: April 2 to April 3
Jacobian matrix calculation | bar: April 3 to April 4
Pseudo-inverse of the Jacobian matrix | bar: May 2 to May 3
Joint velocity derivation | bar: May 3 to May 4
Low-level joint-space controller | bar: May 4 to June 1
Safe and reliable robot operation enforcement | bar: May 4 to June 1
Report | bar: June 2 to August 4